## Sheet1
Week | Task | Work Estimate (in hours) | Status | Start date | End date | Assigned to | Notes
Week1- (06/10) | Create github account, learn to use git with a demo project |  |  |  |  | Ahir Chatterjee
| Play around with drone- setting altitude/speed, geofencing, how accurately can you get it to land |  |  |  |  | Ahir Chatterjee
| Experiment with different recording modes- orbit, follow, selfie, pano, zipline |  |  |  |  | Ahir Chatterjee | 1) Does the drone follow you vertically? Let's say when you climb stairs, does it maintain the altitude?
| Figure out battery life between charge (estd. 20min) |  |  |  |  | Ahir Chatterjee
| Prepare a 4 week plan |  | In progress | 2016-06-06 |  | Rashmi Singh
| Followup with Sanjeev Sisodia for onboarding other engineers | 0.5 | Completed | 2016-06-07 | 2016-06-09 | Rashmi Singh | Sanjeev to get back to us once they are in position to start drivign the initiative.
| Explore image processing options |  | In progress | 2016-06-07 |  | Rashmi Singh | Check if they are available on AWS/Azure
| Create a copy(?) of Tower repository in local account |  |  |  |  | Rashmi Singh
Week2-(06/17)
| Get comfortable flying the drone with Solo app |  |  |  |  | Ahir Chatterjee
| Install Tower app and explore different options |  |  |  |  | Ahir Chatterjee | Requires 3DR services
| Learn to compile and install source code, figure out the relation to 3DR services |  |  |  |  | Ahir Chatterjee
| Explore Solo SDK - can we use it for our requirement |  |  |  |  | Rashmi Singh
| Explore DroneKit - can we use it for our requirement |  |  |  |  | Rashmi Singh
| Off-work | 16 |  | 2016-06-16 | 2016-06-17 | Rashmi Singh
Week3-(06/24)
Make modifications to the Tower app - fly to a specified location, take picture, return (or define specified set of steps)
Understand OpenCV - write sample programs
OpenCV - program to identify parallel parking lines
Week3-(06/31)
Explore OpenCV webservices (Azure/aws)
Write a program to upload pictures from the controller
OpenCV - program to count the number of parking slots
OpenCV - program to identify empty/occupied slots

## Sheet2
Assigned to
Rashmi Singh
Ahir Chatterjee