## Sheet1
Week | Task | Work Estimate (in hours) | Status | Start date | End date | Assigned to | Notes
Week1- (06/10) | Create github account, learn to use git with a demo project | 1 | Completed | 2016-06-07 | 2016-06-09 | Ahir Chatterjee
| Play around with drone- setting altitude/speed, geofencing, how accurately can you get it to land | 0.5 | In progress | 2016-06-08 |  | Ahir Chatterjee
| Experiment with different recording modes- orbit, follow, selfie, pano, zipline | 1.5 | In progress | 2016-06-08 |  | Ahir Chatterjee | Drone does not follow vertically, continues at about its same height from a distance while on "leash" mode.
| Figure out battery life between charge (estd. 20min) | 0.5 | Completed | 2016-06-08 | 2016-06-08 | Ahir Chatterjee | Approximately 15 mins. Does not allow for takeoff after dropping below ~30%
| Prepare a 4 week plan |  | In progress | 2016-06-06 |  | Rashmi Singh
| Followup with Sanjeev Sisodia for onboarding other engineers |  |  |  |  | Rashmi Singh
| Explore image processing options |  | In progress | 2016-06-07 |  | Rashmi Singh | Check if they are available on AWS/Azure
| Create a copy(?) of Tower repository in local account |  |  |  |  | Rashmi Singh
Week2-(06/17) | Get comfortable flying the drone with Solo app |  |  |  |  | Ahir Chatterjee
| Install Tower app and explore different options |  |  |  |  | Ahir Chatterjee | Requires 3DR services
| Look at Tower code and make modifications |  |  |  |  | Ahir Chatterjee
| Explore Solo SDK |  |  |  |  | Rashmi Singh
| Explore DroneKit |  |  |  |  | Rashmi Singh
| Off-work | 24 |  | 2016-06-15 | 2016-06-17 | Rashmi Singh
Week3-(06/24)

## Sheet2
Assigned to
Rashmi Singh
Ahir Chatterjee